## About
EventCraft — Information Security Risk Register
ISO/IEC 27001:2022-aligned risk assessment, self-directed portfolio project
Scope & Subject
This risk register assesses EventCraft, a role-based event management platform built for the Fulda University community as part of the Master Team Project (GDSD program, Hochschule Fulda, Fall/Winter 2025). The assessment is based on the platform's actual documented architecture: React 19 + Tailwind CSS frontend, NestJS + Prisma backend, MySQL database, Socket.IO real-time chat, all containerized with Docker behind Nginx on a single Azure VM.
Methodology
Risks were identified from the platform's documented data entities, authentication/authorization design, and known architectural decisions (see Milestone 2 and Milestone 4 project documents). Each risk is scored using a 5x5 Likelihood x Impact matrix (1=lowest, 5=highest), consistent with common ISO/IEC 27005 risk-assessment practice referenced by ISO/IEC 27001 Clause 6.1.2. Risk Score = Likelihood x Impact. Existing controls are drawn from the platform's actual implementation where documented (e.g., bcrypt password hashing, NestJS ValidationPipe, CORS whitelisting); items marked 'Unverified' or 'Not documented' reflect genuine gaps in available evidence, not assumed controls.
Risk Scoring Legend
Risk Score 15-25 = High ¦ Risk Score 8-14 = Medium ¦ Risk Score 1-7 = Low
Author & Purpose
Prepared by Venkat Bhavan Tati as a self-directed application of ISO/IEC 27001 risk management concepts to a real system, alongside ongoing PortSwigger Web Security Academy and hands-on lab practice. This is an independent learning exercise, not an official audit of EventCraft or an endorsement by the EventCraft project team.
Related documents
- Risk Register (this workbook, 'Risk Register' tab)
- NIS2 Applicability Note (separate document)
- EventCraft Web Application & Network Pentest Report (separate document, in progress)

## Risk Register
Risk ID | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Existing Controls | Residual Risk | Treatment Plan | Owner | Status
R-01 | Azure VM (single instance hosting frontend, backend, DB) | Service outage / denial of service | No redundancy or failover; single point of failure for entire platform | 3 | 4 | 12 | Medium | Docker containerization; Nginx reverse proxy | High | Add load balancer and secondary instance, or migrate database to a managed service | Infrastructure Team | Open
R-02 | MySQL database (Users, Events, Reviews, Loyalty Points) | Unauthorized data access / data breach | Database co-hosted on application VM; protected only by credentials, not network isolation | 3 | 5 | 15 | High | bcrypt password hashing (cost factor 10); DB access restricted to defined ports | Medium | Enable encryption at rest; restrict DB port to internal network only; rotate credentials on a schedule | Backend Lead | Partially Mitigated
R-03 | User authentication (JWT via Passport.js) | Session hijacking / token theft | Intercepted or long-lived JWTs could allow account takeover | 2 | 4 | 8 | Medium | JwtAuthGuard on protected endpoints; Passport.js JWT strategy | Medium | Add short token expiry with refresh-token rotation; enforce HTTPS on all endpoints | Backend Lead | Partially Mitigated
R-04 | Password storage | Credential compromise via offline cracking | Weak hashing could allow rainbow-table or brute-force attacks if DB is exfiltrated | 2 | 5 | 10 | Medium | bcryptjs, cost factor 10; hashes never exposed in API responses | Low | Review hashing cost factor periodically as available compute increases | Backend Team | Mitigated
R-05 | Event banner file uploads | Malicious file upload (web shell / RCE) | Insufficient validation could allow upload of executable content | 2 | 4 | 8 | Medium | MIME-type validation (JPEG/PNG/WebP only); 5MB size limit; UUID filenames prevent path traversal | Low | Add malware/antivirus scanning on upload; store uploads outside the web root | Backend Team | Mitigated
R-06 | Real-time chat (Socket.IO, ChatGroup/ChatGroupMember) | Unauthorized access to private or event chats | Namespace or room misconfiguration could expose chat contents to non-members | 2 | 3 | 6 | Low | RBAC enforcement; ChatGroupMember functions as an explicit access list | Low | Periodic access-list audits; targeted testing of chat authorization logic | Backend Lead | Mitigated
R-07 | Admin panel / Role-Based Access Control | Privilege escalation (Participant/EventOwner reaching Admin functions) | Broken access control if role checks are enforced client-side only, not server-side | 3 | 5 | 15 | High | Server-side RBAC via NestJS guards (per architecture docs; not independently verified) | Medium (unverified) | Formal penetration test of all admin endpoints to confirm server-side enforcement (see Pentest Report) | Backend Lead | Open — pending verification
R-08 | Third-party AI banner generation integration | Data leakage to external service / prompt injection | Event title and description are sent to an external generative-AI API; data handling not documented | 2 | 2 | 4 | Low | Not documented in available project materials | Medium | Review the AI provider's data handling and retention policy; document the data flow | Team Lead | Open
R-09 | CORS configuration | Unauthorized cross-origin requests | A misconfigured allow-list could let malicious sites call the API on a victim's behalf | 2 | 3 | 6 | Low | Explicit origin whitelisting via CORS_ORIGINS environment variable | Low | Review whitelist entries at each deployment; alert on whitelist changes | Backend Team | Mitigated
R-10 | API input validation (event/review submissions) | Injection attacks (SQL injection, stored XSS) | Unvalidated user input on event, review, or profile fields | 2 | 4 | 8 | Medium | NestJS global ValidationPipe; class-validator DTOs; Prisma ORM uses parameterized queries | Low | Add automated SAST scanning to the CI/CD pipeline | Backend Lead | Mitigated
R-11 | GitHub repository / CI-CD pipeline | Supply chain compromise / leaked secrets | A misconfigured or overly public repo could expose source code, secrets, or accept malicious commits | 2 | 4 | 8 | Medium | Secrets kept in environment variables, enforced via code review (see PR history on api.js); separate dev/main CI-CD branches | Low | Add automated secret-scanning (e.g., gitleaks) to the CI pipeline | GitHub Master | Partially Mitigated
R-12 | QR code check-in / attendance data | Forged or replayed QR codes | A predictable qr_check_in_token could allow attendance fraud | 2 | 2 | 4 | Low | Unique qr_check_in_token issued per participation record | Low | Verify token randomness/entropy; add expiry once the event has ended | Backend Team | Open
R-13 | Loyalty points / shop redemption | Business logic abuse (race condition, double-spend) | Concurrent redemption requests could exploit a check-then-act gap in balance logic | 2 | 3 | 6 | Low | Balance re-fetched inside the database transaction before deduction (per code review comments) | Low | Add automated tests for concurrent redemption scenarios | Backend Team | Mitigated
R-14 | Notification system | Notification spoofing or spam / flooding | No documented rate limiting on notification-triggering endpoints | 2 | 2 | 4 | Low | Not documented in available project materials | Medium | Add rate limiting on endpoints that trigger notifications | Backend Team | Open

## Summary
EventCraft Risk Register — Summary
Total risks identified | 14
By Risk Level
High | 2
Medium | 6
Low | 6
By Status
Open | 5
Partially Mitigated | 3
Mitigated | 6